## Sheet1
ACTION PLAN - 2014
10th Public Procurement Knowledge Exchange Platform
Hilton Istanbul Bosphorus, Cumhuriyet Caddesi Harbiye, Istanbul, 34367, Turkey
Hosted by the Public Procurement Authority of Turkey
S.N. | Country | Recommended | Achievements in 2011 | Action Plan for 2012 | Achievements in 2012 | Action Plan for 2013 | Achievements in 2013 | Action Plan for 2014
Actions in 2011
1 | Albania | 1) e-shopping to be adopted by 2012 | 1) e-shopping to be adopted by 2012 – still ongoing, not yet achieved, but by the end of 2012 will be entered in the system | 1) e-shopping will be done by 2012 and e-auction will also be completed with the assistance of EBRD. | 1. Regulatory framework and new law on concessions | 1) Develop a complains module in the electronic system | 1) Concession and PPP Law No. 125/2013 - secondary legislation on concessions/PPP. On the action plan for 2013, the four activities included were related to the electronic system. The only achievement to be reported is the electronic conduction of first phase of Concessions and PPPs procedures. First phase includes electronic publication of concessions and PPP procedures and electronic bidding. As regards the other three activites, no measure was undertaken, since the previous year was an electoral one. After the new government came into power, it was set up a working group on analysing the electronic system, which will define what will be the next appolications to be added to the system. | 1) Preparation of the National Strategy on public procurement in cooperation. This will done in cooperation with SIGMA.
[5 empty] | 2. Increase of transparency of electronic services and concessions | 2) Concessions and PPPs will be fully conducted electronically | 2) The only achievement to be reported is the electronic conduction of first phase of Concessions and PPPs procedures. First phase includes electronic publication of concessions and PPP procedures and electronic bidding. | 2) Preparation of some amendments to the Public Procurement Law (PPL).
|  | 2) introduction of framework agreements in e-GP | 2) introduction of framework agreements in e-GP – first phase is already designed in the system and the users can use it | 2) Second Revision of the FA is in progress and will be completed by end of 2012. | 3. Capacity building – structure of PPA increased | 3) Evaluation of PPPs in e-GP system | 3) As regards the other three activites, no measure was undertaken, since the previous year was an electoral one. After the new government came into power, it was set up a working group on analysing the electronic system, which will define what will be the next appolications to be added to the system.
[5 empty] | 4. Training of 856 staff from contracting authorities on the current procurement legislation; | 4) E-Auction and FA will be introduced
|  |  | 3) first phase of e-concessions done through the system | 3) Changes to the PPL will be done by 2012 and draft on Public Private Partnership (PPP) and concessions will be included in the law
2 | Armenia | 1) Full implementation of e-GP. | 1) Full implementation of e-GP – All the tasks implemented, but in practice we will improve some aspects related to e-purchase. | 1) To build and improve capacity in the county and involving local authorities in using the e-GP. | 1) E-GP has been partially introduced | 1) Fully deployment of e-GP | Both actions envisaged under 2013 actions plan has been achieved. 1) Starting from 2013 all open tenders are conducted in e-procurement system. Starting from 2014 – same system is used for framework agreements. | 1) Improvements to the E-Procurement system by adding modules for (i) e-procurement planning, (ii) contract monitoring and (iii) progress reporting.
|  | 2) Finalization of institutional reforms. (Procurement Appeal Board and Procurement Support Center) | 2) Finalization of institutional reforms. (Procurement Appeal Board and Procurement Support Center) | 2) Training through universities and institutions from Italy and Portugal. | 2) Support Center for e-GP introduced | 2) Introduction of Commodity classification | 2) CPV codes have been developed in 2013 and procurement plans are prepared based on CPV codes. | 2) Amend the law on public procurement of republic of Armenia and to align the same with (i)Agreement of Customs Union on procurement and (ii) WTO
3) Requesting funds from donors for the training.
3 | Azerbaijan | 1) preparation of regulation on e-signature | 1) e-Government was improved. Government works on foundation of information security board and under the law act on e-signature. | 1) State Agency of Procurement wants to make Pilot projects with e-GP. | 1) e-signature established | 1) Fully on-line Procurement Planning | 1) The new law has been discussed with different authorities and introduced to the presidents administration for approval. The new law provides such innovations as: (i) Procurement Plans; (ii) E-Procurement; (iii) Official Contracts registry base; (iv) Non-reliable suppliers registry | 1) Pending approval of new law
|  | 2) training of public and private sector with the help of training institutions (in partnership with Turkey?) | 2) Training of public and private sector with OECD/SIGMA were conducted. | 2) Continue training with OECD/SIGMA, WB, EBRD, UNCITRAL and USAID. | 2) Procurement Planning introduced | 2) e-GP will be fully introduced by end of 2013. | 2) Prepared draft methodology for establishing cost estimation. | 2) E-GP procedures/instructions prepared following approval of the law. (for 2015 MOF has officially confirmed allocation of approximately US$ 600,000 for creation and development of e-procurement system)
|  | 3) Further improvements to PPL in consultation with MDBs | 3) Further improvement were made in consultation with ADB and USAID. | 3) After discussion with UNCITRAL on the PPL, suggestions will be taken to the Government by SPA. | 3) Training in Public Procurement with OECD/SIGMA completed ad will continue | 3) Cost estimation guidelines will be introduced; | 3) All contract award results are being published in SPA website. | 3) Preparation of guidelines for cost estimation.
[5 empty] | 4) Amendments to the PPL were drafted, but not yet approved; | 4) Supplier performance database will be established and non-reliable suppliers will be published; | 4) Online procurement planning is exercised by majority of contracting authorities, but the same will be mandatory once the law is approved.
[5 empty] | 5) Study tour to Poland, with SIGMA assistance, to learn about Polish public procurement system; | 5) Complaint handling will be strengthened;
6) All contract award results will be published in SPA website;
4 | Bosnia and Herzegovina | - | 1) Prepared new draft PPL | 1) New PPL to be adopted in 2012 | 1) Electronic registry of Procuring entities | 1) New PPL to be adopted in 2012 | 1) The new PPL has been adopted in April 2014 | 1) Preparation and adoption of by-lows [ 12 regulations] related to new (2014) PPL
|  |  | 2) start publishing electronic notices | 2) Prepared implementation regulations in accordance with the new PPL |  | 2) Prepared implementation regulations in accordance with the new PPL | 2) Having in mind that new PPL has already been adopted, preparation of implementation regulations in accordance with the new PPL started in May 2014. | 2) Preparation of (draft) standard bidding documents related to new (2014) PPL
|  |  | 3) prepare annual reports and report about monitoring | 3) prepare all activities to create software for e-auctions and continue developing platform for e-procurement. |  | 3) Prepare all activities to create software for e-auctions and continue developing platform for e-procurement. | 3) Software development is in progress. Register /data base / of contract authorities and suppliers is completed. | 3) Complete software development related to e-auction and e-tendering
[6 empty] | 4) Capacity building and new rule book on internal organization and job classification | 4) New rule book is finalized, and in procedure for its adoption. | 4) Create new public procurement portal
[6 empty] | 5) Recertification of accredited trainers and updating the registered trainers list; | 5) Finalized in October 2013 (supported by GIZ) | 5) Complete training of : (i) PPA and PRB staff, (ii) BiH court, (iii) Trainers, and (iv) Auditors
5 | Croatia | [6 empty] | 1) Further development of e-procurement, especially the e-submission of bids. Starting with 01.01.2015, all bids submitted to central purchasing office should be submitted electronically.
7 | FYR Macedonia | 1) reaching to50% level for use of e-GP (e-auctions) | 1) Reaching to50% level for use of e-GP – we have reached 49% of e-auctions, so it is done. | 1) reaching to100% level for use of e-auctions | 1), 2) and 3) achieved. | 1) Upgrading e-GP with new functionality with contractor profile | 1) Upgraded ESPP with new functionality with EO profile. | 1) To upgrade the ESPP to a mobile version
|  | 2) implementation of training program for 2011 | 2) Implementation of training program for 2011 – was implemented as planned. 18-20 training with 300 people trained. | 2) Introduction of mandatory certification of procurement officers. |  | 2) Mandatory publication of tender documents and it can be downloaded free. | 2) Mandatory publication of TD | 2) Strengthening the institutional capacity of the PPB.
|  | 3) providing self-sustainability in terms of financial independence (generate more funds by increasing the base) | 3) Providing self-sustainability in terms of financial independence (generate more funds by increasing the base) – is done recently. We started charging from April, so e-GP is sustainable. | 3) Mandatory publication of low value contracts below 5,000 Euro. |  | 3) Increase the share of procurement on e-GP | 3) Increased procedures conducted electroically. In 2013 - 15% | 3) Increase the e-procurement procedures.
4) Improve contract management.
8 | Georgia | 1) translation of e-GP system into English | 1) translation of e-GP system into English – Done. | 1) Finalization of two stage tender. | 1) Two stage tendering implemented in the system completely; | 1) The e-GP system shall be available in 5 languages (Georgian, English, Armenian, Russian, Turkish) | 1) Creation of separate module for conducting tenders under the World Bank financed project for civil works/good under NCB procurement method. (Depended on the outcome of above initiative, the system would equally accommodate request from other IFIs to launch the similar module under their projects) | 1) Creation of separate module for conducting tenders under the World Bank financed project for civil works/good under NCB procurement method. (Depended on the outcome of above initiative, the system would equally accommodate request from other IFIs to launch the similar module under their projects)
|  | 2) translation of User Manual into English | 2) translation of User Manual into English – It is translated | 2) By the end of 2012 full SBDs online. | 2) Standard bidding Documents partially developed; | 2) Develop contract monitoring module in the e-GP; | 2) Contract monitoring module is fully developed in the e-GP; System reflects all payments done under the contract as well as the statuses of contract (Completed, ongoing, terminated). In addition all subsequent documents during the contract execution - (delivery acceptance acts, amendments, interim payment certificates) are also uploaded in the system. No payments can be processed by e-treasury unless the contract is registered within the contract monitoring module. | 2) Developing system based module for conducting design contest with pre-defined quantifiable evaluation criteria based on formula.
|  | 3) Finalization of Business Intelligence Module | 3) Finalization of Business Intelligence Module – Developed and finalized. - 70 real time reports | 3) All data in the system will be web-based. | 3) All data in the system is web-based (all contracts are included in the system) | 3) Develop unit price module for goods; | 3) Unit price module for goods is developed which contains all unit rates under the respective contract and exact description of the goods, including manufacturer, make/model, specification and quantity. All such information comprises unique database and can be processed in e format. | 3) Subject to availability of financing from Word Ban/IFis, enhancing operation of competence center through provisions of equipment and conducting training for contracting authorities and suppliers.
|  | 4) Creation of analytical department within SPA | 4) Creation of analytical department within SPA – It is created but is called analytic group. |  |  | 4) Web-based conclusion of contracts; | 4) All contracts are reflected in contract monitoring module. | 4) Creation of two stage bidding module and gradual development for CPV codes envisaged under the legislation.
|  | 5) introduction of two-stage electronic bidding (first technical evaluation and then electronic reverse auction) especially for consultancy services | 5) introduction of two-stage electronic bidding (first technical evaluation and then electronic reverse auction) especially for consultancy services – under development, We are in the testing mode and in a few months we will launch it and it will be fully operational |  |  | 5) Establish the public procurement competence center; | 5) The legal part of establishing the public procurement competence center is fulfilled and reflected in the decree and structure of the Agency; competence center will be fully operating once SPA shifts to new planned towards end of September 2014.office
|  | 6) improvements in HR system in SPA | 6) improvements in HR system in SPA – we have a contract with a major HR company in Georgia. It is done but the process will never end.
|  | 7) Collaboration with Competition Agency | 7) Collaboration with Competition Agency – We did that. All PP are available through different methods.
8) introduction of online procurement plans
9) introduction of web-based SBDs
9 | Kazakhstan | 1) amend the PPL to introduce e-auction in collaboration with WB-JERP financed study | 1) the JERP study has been completed and the PPL has been amended in 2012; |  |  | 1) Further changes to procurement legislation in terms of sole source procurement and introduce tenders in electronic form; | 1) Plan for year 2013 has been implemented | 1) Present the new Public Procurement Law to the Parliament
|  | 2) piloting of e-auction by the end of 2011 | 2) the piloting of e-auction is completed;
|  | 3) amend the secondary legislation for e-auction | 3) The amendment of the secondary legislation for e-auction is completed;
10 | Kosovo | - | 1) PPL approved | 1) Publication of all tender dossier online | 1) The publication of all tender dossier is yet to be completed; | 1) Implementation and piloting of e-procurement system and by 2015 use the e-procurement system; | 1) Evaluation of hiring a vendor to develop e-GP platform has been completed as of May 29, 2014 and still on track to implement and pilot e-GP by March 2015 | 1) To complete e-GP system by March 2015. Pilot will be carried out in January 2015 in five to six contracting authorities who have better IT infrastructure. Selection of the CAs will be done by PPRC
|  |  | 2) Secondary legislation approved including regulation for | 2) Piloting e-procurement | 2) Development of the e-procurement system is ongoing (TORs for the system are drafted, within the coming month the procurement process shall be launched); | 2) Develop the 5-year Public Procurement Strategy | 2) Prepared a draft 5-year public procurement strategy. The draft is in discussion with all stakeholders and will be finalized by PPRC in October 2014 | 2) Complete overall National Public Procurement Strategy for Kosovo by October 2014
|  |  | 3) 489 trained. | 3) Complete training of 30 trainers for public procurement funded by EC | 3) The PPL includes a chapter for the monitoring of contract implementation, all related secondary legislation is in place; | 3) Training strategy for the procurement officers; | 3) Completed Training strategy for the procurement officers in April 2014 and will become the core material for training public procurement officers in the future | 3) Finalize the manual for Monitoring Performance in Public Procurement system in Kosovo by December 2014
|  |  |  | 4) To develop the Public procurement strategy for next 5 years | 4) The overall secondary legislation for the PPL implementation is in place; | 4) Design the Public Procurement Compliance and Performance Monitoring System in Kosovo (WB assistance) | 4) Draft Manual has been completed for the Public Procurement compliance and Performance Monitoring system in Kosovo. PPRC with the help of consultants have started piloting the monitoring of performance (with two contracting authorities namely Ministry of Health and Ministry of Youth) | 4) Continue Training of Public Procurement Officers on a regular basis
|  |  |  | 5) To develop national strategy for training of public officers. |  | 5) Develop the unit price database for goods, services and works; |  | 5) Start amending of current Procurement Law by December 2014
6) Development of the centralized purchasing system within the Central Purchasing Agency (initially for fuel and IT equipment);
11 | Kyrgyz Republic | 1) Revisions to secondary legislation | 1) Revisions to secondary legislation. SBDs reviewed and prepared which is now with the Government. | 1) Hiring of international procurement consultant (lawyer). | 1) Completed | 1) Improvement of the legislative framework (new draft PPL- orient the PPL towards the use of e-procurement, complaints); | 1) Improvement of the legislative framework (new draft PPL prepared and submitted to the Parliament); | 1) Adopt new PPL and related regulations;
|  | 2) training related to changes in PPL by the training center under MOF | 2) training related to changes in PPL by the training center under MOF – Conducting training based on the changed PPL and bylaws. | 2) Establish a working group to discuss and prepare revisions to PPL and secondary legislation on introduction of e-GP. Hiring of international procurement lawyers to assist the working group to revise the PPL. | 2) Completed | 2) Review of secondary legislation | 2) Secondary legislation is prepared, ready to be approved once new PPL is adopted | 2) By the end of the year put in place electronic reverse auctions and e-catalogue;
|  | 3) concrete action plan for e-GP | 3) concrete action plan for e-GP – Has been prepared and passed for approval to the Government. | 3) Ensure that 100% of procuring entities use PP web-portal for advertising and contract awards and launch of procurement; | 3) Partially completed | 3) By the end of the year put in place electronic reverse auctions; | 3) First phase of E-GP system is developed. First electronic tender will be launched on June 3, 2014. | 3) Improve collection of statistical date along with its analysis and prepare improved statictical report for 2014.
|  |  |  | 4) Prepare annual reports for public procurement for 2011. | 4) Completed | 4) Create an independent commission for review of complaints; | 4) New PPL has provision for an independent commission for review of complaints; | 4) Finalize guidance on the implementation of the public procurement legislation.
[6 empty] | 5) Guidance on the implementation of the public procurement legislation ; | 5) Procedure for the framework agreements is prepared.
6) Develop the procedure for the framework agreements;
12 | Moldova |  | 1) PPL changed and transparency increased (all procedures to be published | 1) Capacity building on e-procurement (workshops), all CAs will be trained on CP. Workshops on implementation | 1) Established the CPV indices (100 % completed); | 1) Modifying the number of procedures and contracting authorities that will participate in electronic procedures; | 1) Number of contracting authorities has increased to 98. These include central public authorities, ministries and bodies subordinated to them. These are the biggest procurement entities which carry out 28% of the entire public procurement; | 1) Improve the existing statistical module;
|  |  | 2) CPV regulations were approved. | 2) To be approved in 2012, regulations and all achievements of 2011 | 2) Complaints procedure by electronic means was completed 100%; | 2) Organize training events for all participants from contracting authorities that will use the electronic procurement; | 2) As part of implementing the order of the Ministry of Finance, the training plan has been developed. The training of contracting authorities has been carried out online, in groups of 5-7 people. Working groups, including training, have been created for economic operators; | 2) Develop a more complex analytical module which will allow us to process all the collected data. This will give us the possibility to follow the trend in each sector and redirect it, if needed;
|  |  | 3) Training was conducted | 3) Pilot Project on e-GP and particularly on e-notification and its assessment |  | 3) Modify the primary and secondary regulatory framework to fully harmonize with international standards; | 3) The PPL has been adjusted to the EU Directive No. 18/2004. The draft is currently being examined by parliamentary commissions. New draft law on utilities has been developed. The regulations and Standard Bidding Documents needed for conducting public procurement using e-GP have been approved. | 3) Ensure transparency in each step of the procurement process, starting with the needs assessment step, financial planning and, most importantly, ending with the contract implementation monitoring.
13 | Montenegro |  | 1) Adoption of new PPL and secondary legislation | 1) Further implementation of the new PPL, strengthening of capacities for main stakeholders and public officers. Training accordingly to the new PPL of main stakeholders and public officers |  |  | 1) EC screening for Chapter 5 on Public Procurement is adopted. | 1) The IPA funded project "Implementation of e-procurement" with cost estimated to Euro 1.5 million is planned to be conducted.
|  |  | 2) Strategy and follow up action plan 2011-2015 adopted | 2) EU project (1 year) focused on developing technical specifications for the e-GP. |  |  | 2) Negotiated position in field of public procurement circulated to council on Oct. 14, 2013 | 2) Adoption of the amendment of the PPL and improvement of principles of public procurement.
|  |  | 3) Introduction of e-notification portal. |  |  |  | 3) The 3-rd meeting of the Accession Conference with Montenegro at a ministerial level held on Dec. 18, 2013 in Brussels to open negotiations on Chapter 5 Public Procurement | 3) Implementation of training session and strategy of public procurement, especially in regard to anti-corruption and conflict of interest.
[7 empty] | 4) Within IPA financed project "Training in Public Procurement in Western Balkans and Turkey", the country was recognized with a certificate and a team of 12 procurement trainers was established. | 4) Montenegro is officially an EU candidate country. Other steps in the action plan will be complementary with new trend in the level of EU.
[7 empty] | 5) The project "Strengtheing of public procurement system in Montenegro" was conducted in June 4, 2012 to July 2, 2013, where 4 experts in law, IT, audit/inspection in public procurement were engaged in the above project. | 5) Together with the EU Commission we will set up new goals and related activities to achieve them.
14 | Romania | [6 empty] | 1) Upgrade the e procurement system (SEAP) ingluding to enable better monitoring of the procurement process;
2) To transpose the new EU Directives in the local legilsation by April, 2015 and to monitor performance
14 | Russia |  |  |  | The PPL has been enacted but will enter into force in January 2014 | 1) The new PPL to enter into force in January 1, 2014; | 1) New Public Procurement Law was adopted and came into force on January 1, 2014 (Federal Law 44-FZ). MinEcon and MinFin have developed and the Government has adopted 37 normative legal acts required for implementation of the Law; | 1) To insert revisions into Federal Contracting Law 44-FZ to introduce e-procurement (with exception to single-source procurement);
[6 empty] | 2) Implementing regulations to be drafted by the time of entry into force of the PPL; | 2) Regulation for planning of purchases was developed for 3-year period; | 2) To insert a requirement to justify procurement during planning stage taking into account normative expenditures;
[6 empty] | 3) Develop 3 year procurement plans in accordance with the new PPL; | 3) Starting from 2014 cenralized purchasing under 44-FZ is being implemented. | 3) Definition of an order for monitoring contracts (including participation of banks) in terms of anti-corruption legislation;
[6 empty] | 4) Centralized procurement, envisaged under the new PPL, is expected to be implemented by 2014. |  | 4) To develop and adopt acts (sub-laws) of Government required for further realization of 44-FZ Law (26 acts);
5) To develop (by the end of 2015) a unified procurement information system;
6) To consider a possibility to develop criteria (if not yet done by Accounting Chamber) for measuring effectiveness of procurement.
16 | Slovenia | [6 empty] | 1) Prepare a substantial analysis of public procurement system to determin good and bad practices of elements of pubic procurement procedure and the most frequent and recurring breaches of law and develop new indicators to measure transparency and efficiency of public procurement process, economic spending of public funds, application of proportionality in public procurement, accountability, penetration of foreign suppliers, works and service providers in Slovenian public procurement market, level of SME participation, etc.
17 | Serbia | - | 1) Introduced certification process of public procurement officers. More than 1000 PP Officers were certified (63% passed the exam) | 1) Improve of public procurement web-portal (i) introduction of CPV in Serbian version (ii) advance searching of Public Procurement announcements by which bidders will be informed immediately of tenders that they have been registered for (iii) improve call centers timing within 3 hours (iv) enable publishing of annual Procurement Plans by contracting authorities. (v) improve announcement of low value procurement and tender document. | 1) New PPL and a number of by-laws were adopted; | 1) Introduce pilot project for e-procurement;
|  |  | 2) System of CPV searching engine were installed in the web-portal in English. Translation will be done by end of 2012. | 2) Start with introduction of e-tendering pilot project with chosen contracting authorities and specific subject of procurement. | 2) The PP portal was improved by introducing new functionalities and features (obligatory use of CPV, more advanced search of public procurement notices, obligatory publishing of all contract notices, obligatory publishing of small value procurement, publishing of list of contracting authorities, exemptions, prior opinions of PPO on negotiated procedures, successfully implemented the TOT regional project, twinning project with Danish and Slovenian counterparts, new commission of complaints review was recently appointed); | 2) Develop the registration system for the economic operators;
|  |  | 3) Three tools were added to the PPO web-portal, (i) CPV codes; (ii) test of knowledge of public procurement and (iii) public procurement planner. | 3) Start with the process of joining PEPPOL projects. |  | 3) A number of by-laws to be adopted in the second part of 2013;
|  |  | 4) Adoption of strategy (September 2, 2011) on future development of public procurement system in Serbia. |  |  | 4) Make amendments to the overall PP action plan in line with the new PPL;
5) The e-auction system to be implemented;
6) Accreditation of public procurement officers in accordance with the new PPL;
7) Establish the central register of economic operators to verify their eligibility for participation in public procurement ;
8) 'Develop new manual for the conduct of new procedures such as competitive dialogue,
9) Develop a new electronic system of quarterly reports for XXXXX
10) Develop a new electronic system for the submission of annual plans by the contracting authorities to the PPP and supreme audit institution;
18 | Tajikistan | 1) study tours to countries implementing e-GP | 1) study tours to countries implementing e-GP – Partially done, visited Albania | 1) Introduction by the end of 2012 with the applications method with some of the e-procurement for pilot ministries, with the help of WB. |  |  | 1) Revision of the PPL initiated; | 1) Prepare new draft PPL;
|  | 2) electronic publication of procurement notices and contract awards | 2) Electronic publication of procurement notices and contract awards – Done. | 2) Organize training with the support of WB for the PPA officials |  |  | 2) e-GP national strategy for 2013-2015 developed and adopted; | 2) Train the trainers, public & private sector with support of PFM Grant;
|  | 3) include Public Utilities and Government Owned Enterprises into the scope of PPL | 3) include Public Utilities and Government Owned Enterprises into the scope of PPL – more that 50 %, partially implemented, with some lined ministries, some state companies | 3) Full involvement of Government Owned Enterprises in the public procurement |  |  | 3) e-quotation module piloted (procurement of fuel, oil and lubricants); | 3) Design the Public Procurement Performance Monitoring System and prepare annual reports;
|  |  |  | 4) Prepare annual report for 2011 public procurement and publish them on e-GP portal. |  |  | 4) PPA portal renewed and launched. | 4) Continue developing e-quotation module with support of IDF Grant;
5) Improve PPA portal by introducing new functionalities and features;
6) Strengthen complaint handling mechanism
19 | Turkey | 1) continue to share experiences with other countries in collaboration with MDBs |  |  | 1) Continue experience exchange with other countries (Korea, Kosovo, etc); | 1) Continue experience exchange with other countries in collaboration with MDBs and other donor organizations; | 1) Considering 2013 action plan, PPA has signed a MoU with Korean Public Procurement Service (PPS) and started training program for increasing e-procurement capacity. Furthermore, close cooperation with international organization has been continued increasingly. | 1) Continue information sharing and experience exchange with other countries (Yemen, Oman etc.)
|  | 2) certification/licensing of private sector especially on construction sector |  |  | 2) Certification of economic operators by adopting a new law (not yet enacted); | 2) Establish a certification system for the economic operators (if the PPL is enacted by the Parliament) | 2) As for the technical achievements, PPA is progressing step-by-step strategy for the establishment of certification system for the tenderers. As a remarkable step, the work experience certificate can be provided by EKAP (electronic public procurement platform) currently. | 2) If the PPL is enacted by the Parliament, certification system will be designed more comprehensive.
[5 empty] | 3) Developed electronic submission and evaluation of bids in all sectors not yet fully completed; | 3) Use of e-procurement in all types of procurement (goods, works and services) focused the submission and evaluation of bids | 3) EKAP's capacity has been increased significantly and electronic bid submission and evaluation can be obtained by EKAP for second stage of framework agreements. | 3) Procurement performance indicators and objectives will be revised using international organizations' methodology and objectives.
20 | Turkmenistan | 1) Adoption of PPL | 1) Adoption of PPL – under consideration of Parliament and to be adopted by 2013. | 1) Adoption of the PPL | None of the actions for 2012 were completed; | 1) Adoption of the PPL | 1) New PPL has been adopted. | 1) To get this new PPL adopted by the Parliament and develop secondary legislation.
21 | Ukraine | - | 1) Amendments of PPL regarding the approach of the Public owned companies to procurement | 1) Enter into force the secondary legislation | 1) Introduced the framework agreements; | 1) Establish the strategy for public procurement; | 1) Strategy for public procurement approved by the Cabinet of Ministers regulation in August 2013 and as a part of the PFM strategy for Ukraine; | 1) Join GPA;
|  |  | 2) legal grounds for framework agreements, simplifications in single source procedure | 2) Strengthening of capacities regarding the web portal |  | 2) Introduction of e-procurement system (including the framework agreements); | 2) E-procurement tools are provided for in the current PPL enacted in April 2014, which is in line with EU Directives. Currently all notices are done electronically (printed version is discontinued). Bidding Documents are distributed electronically, information on contract amendments and contract completion. Framework agreements were piloted for Health Sector procurement of food and coal; | 2) Use e-procurement tools in practice;
|  |  | 3) Ratification of FTA agreement with EFTA | 3) Adoption of the PPL regarding Utilities , public undertaking. |  | 3) Possibly establish an agency for centralized purchasing; | 3) No. Establishment of the centralized purchasing Agency is being considered as a part of rolling out of Framework Agreements. | 3) Collaborate with CSOs in improving public procurement legislative framework and functioning.
4) Negotiations with EU on FTA completed.
22 | Uzbekistan | 1) Continue to work on draft PPL to simplify procedures |  |  |  |  | 1) Regulation of the COM “Regulation on organization and conducting the e-procurement(e-reverse auction) at the UzRTSB”, dated November 06, 2013; | 1) Development and approval of the “Uzbekistan - Public Procurement Development Strategy/Concept till 2025 (August, 2014);
[7 empty] | 2) New Budget Code has been adopted considering the issues related to the Public procurement. | 2) Development and discussion of the Public Procurement Law with the involved ministries (December, 2014);
3) Revision of the PP regulations (end of 2014)