## Slide 1: 2nd South Asia Regional Public Procurement Conference Islamabad, Pakistan, (March 25-27, 2014)
Key Actions Agreed in Kathmandu Forum (2011) and Progress Status
Chandra Man Shrestha, Joint Secretary
Public Procurement Monitoring Office (PPMO)
Kathmandu, Nepal

## Slide 2: Key Actions Agreed in Kathmandu Forum (2011) & Progress Status
1.1 SAR Common Platform related Actions (8/17)
Agreed Actions | Progress Status
1. Creation of SARPPCG (1) | An informal group of SAR PP heads formed, met several times through GDLN.
2. Hold SAR Forum Every year (2) | 1st Forum Held in KTM (Apr26-28,2011) 2nd – Now in Islamabad (Mar25-27,2014) Every 2 year would be appropriate
3. Creation of SAR Web portal (3) | Initiated creation, but yet to be completed. Source of financing to be identified.
4. Development of SAR Mechanism for sharing experience/ lesson learned (4) | Linkedin Group (closed) created by PPMO/Nepal for SAR Public Proc. Heads/officials, ADB & WB experts. GDLN is being used as a common platform.
5. Integration of SARPP Topic in SAARC (13) | With PPMO/Nepal initiative, concept circulated by SAARC Secretariat to all 8 member countries and positive responses received.
6. SAR Arbitration Center(11), Pvt Sector Forum(12) & W-shop/Seminar at SAR level(17) | 11 – Pending - Too soon 12 - Done in Bangladesh only 17 – Pending - Not done except GDLN

## Slide 3: Key Actions Agreed in Kathmandu Forum (2011) & Progress Status
1.2 Capacity Bldg./Professionalization related Actions (5/17) …
Agreed Actions | Progress Status
1. Development of Training Modules (7) | Bangladesh – 3 wks module under impl-n WB India is finalizing online e-modules for procurement training
2. Proc. Professionalization/ cadre in Civil Service (10) | Pending Bhutan has done something
3. Accreditation of proc. Staff(9) | Bangladesh – BRAC Univ. & CIPS/UK collaboration PPMO/Nepal has initiated process
4. University level procurement curriculum (6) | Bangladesh – BRAC Univ. & CIPS/UK collaboration
5. Identification of SAR Training Institutions (8) | Bangladesh – Proc. faculty in Eng. Staff College India & Nepal – just initiated

## Slide 4: Key Actions Agreed in Kathmandu Forum (2011) & Progress Status
1.3 Proc. Tools/ Standards/ Process related Actions (4/17) …
Agreed Actions | Progress Status
1. Promote e-Procurement (14) | e-Proc. in Bangladesh (full fledged in limited PEs) e-proc. in Nepal (e-Submission in limited PEs) e-proc. in India (in 2 states?) e-proc. in Afghanistan/Bhutan/Maldives/Pak/ Srilanka/?
2. Promote new methods – PPP, EPC (15) | PPP in India in Highways Ktm-Hetauda Tunnel Road, Nepal
3. Modernize contract management (16) | Pending – but slowly ongoing
4. Harmonize standards across SAR (5) | Pending – Too soon

## Slide 5: Way Forward
To be continued with emphasis:
  Hold SAR Conference every 2 years
  SAR web portal – Upgrade and maintain
  Linkedin Group – maximize use
  Integration of SARPP topic in SAARC – Apply more effort to make it happen.
  Pending Actions of Kathmandu Forum – Discuss for their relevance & choose for future actions on priority basis (Next session)
Areas of Focus – To be strengthened & New
  SAR Training institutions and training modules –
  Promote e-Procurement –
  New/emerging methods – PPP, EPC/DB, Framework Agreement & others

## Slide 6
  Thank You