## Slide 1: Debt Management Facility Briefing
Abha Prasad
DMF Program Manager and Senior Debt Specialist
Economic Policy and Debt Department
The World Bank
May 6, 2014

## Slide 2: Contents
DMF I – 5-years of implementation
DMF II -Multi-donor Trust Fund
  Expanded Activities Coverage
  Country coverage
  Governance arrangements
  Contributions and commitments
Findings from TA activities and how that shapes DMF II work program

## Slide 3: DMF 1: Program Implementation (1) Activity wise
* up to April 2014
Move towards formulation of debt management strategy
Increase in capacity building trainings

## Slide 4: Program Implementation (2) Capacity Building -Trainings
Training by Type
Training by Region

## Slide 5: Program Implementation (3): Diversity (DeMPA, Reform Plan and MTDS)

## Slide 6: Program Implementation (4) (Planned vs Actuals: inception to April 2014)
DMF Program implementation January 2009-June 2014 | Planned till June 2014 | Actual till April 2014
Total missions | 183 | 134
of which DeMPA missions | 82 | 54
of which MTDS missions | 66 | 45
of which Reform Plan missions | 35 | 35
Training events | 32 | 42
DMPP | 24 | 24
DMN | 8 | 8
Stakeholders Forum | 5 | 4 (+1)*
* Fifth in April 2014

## Slide 7: DMF II- Multi-donor Trust Fund Launched
DMF II launched on April 4, 2015 in partnership with IMF
Builds on basic principles of DMF I
  Programmatic approach
  Sustained engagement
  Promote collaboration among wide range of institutions and partners
  Builds on strong partnership with IMF
  to leverage institutional expertise
  to deliver capacity building in debt policy and management
    Working together on debt relief and debt sustainability initiatives, and technical assistance on medium-term debt management strategy (MTDS) formulations

## Slide 8: Expanded Coverage of Activities
Current DMF Activities to be continued
DeMPA
Debt Management Reform Plans *
New Activities
DSF- capacity building*
Debt Managers’ Network Peer Learning Activities
Advice on Domestic Debt Market Development*
MTDS *
Debt Managers’ Network and Peer Learning Activities
Debt Managers Practitioners’ Program
Debt Portfolio Risk Management
International Capital Market Operation – advice on issuances
Knowledge generation and dissemination*
Subnational debt management*
*Activities will be carried out jointly for both the Bank and IMF, and Implementing Partners.

## Slide 9: Country Coverage – Similar to DMF I
All IDA-eligible countries, LICs and those that have graduated but were part of the initial program
IMF’s Poverty Reduction and Growth Trust countries
    a sub-set of LICs

## Slide 10: Governance Arrangements
Steering Committee
  Donor representation - one representative of each donor (contributions of USD 1 million over a 2-year period)
  Co-chairs WB and IMF
  Endorses work program, Reviews reports
Secretariat
  Manages day-to-day operations
  Coordinates with donors, IMF and implementing partners
  Complies annual report (and log-frame report)
Panel of experts
  Advising and quality review
Implementing Coordination Group
  Coordinates partner activities

## Slide 11: Contributions and Commitments
Existing donors spearheading financing efforts
  Austria
  EU
  Germany
  Netherlands
  Norway
  Switzerland
Administration Agreements finalized with 3 donors and funds transferred to DMF II.
Potential commitments and interest from the Asian Development Bank, the EU, France, Russia and Sweden
Support down the pike likely from – the African Development Bank, Belgium, and Canada
Exploring interest from Australia, Denmark, the European Investment Bank, Korea, and Luxembourg

## Slide 12: What have the DeMPA results shown us?
Note: The chart is based on the results of 62 sovereign DeMPA reports
Chart: 
| Legal framework | Managerial Structure | Debt Management Strategy | Evaluation of Debt Management Operations | Audit | Coordination with Fiscal Policy | Coordination with Monetary Policy | Domestic Borrowing | External Borrowing | Loan Guarantees, On lending Derivatives | Cash Flow Forecasting and Cash Balance Management | Debt Administration and Data Security | Segregation of Duties, Staff Capacity and BCP | Debt Records | Debt Reporting
Meet with the requirements of Score C or Higher Scores | 35 | 40 | 12 | 28 | 5 | 27 | 37 | 38 | 12 | 20 | 12 | 10 | 5 | 30 | 14
Not meet with minimum requirements | 28 | 23 | 51 | 35 | 58 | 36 | 26 | 12 | 50 | 37 | 51 | 53 | 58 | 33 | 49

## Slide 13: What have the MTDSs shown us: Average values of risk indicators
Chart: Weighted average interest rate external
| LIC | LMIC | UMIC
Min-Max | 3.1419 | 4.8205 | 8.3275
 | 0.39467 | 0.871 | 2.0426
Average | 1.2371 | 2.0724 | 4.8216
Chart: ATM external
| LIC | LMIC | UMIC
Min-Max | 21.0687 | 16.4027 | 8.9089
 | 10.4143 | 6.5596 | 4.4
Average | 15.8442 | 11.5909 | 7.5472
Chart: FX debt (% of total)
| LIC | LMIC | UMIC
Min-Max | 97.3717 | 100 | 83.5
 | 44.7175 | 13.382 | 32.6947
Average | 71.5183 | 69.3634 | 59.0294
Source: WB Internal Study

## Slide 14: Progress Made: Early Outcomes
DeMPA Indicator | Steps taken | Country | 
Legal framework | Strengthened legal framework | Burundi, Malawi, Sierra Leone, Togo, Mongolia, Sao Tome Principe, Sierra Leone | 
 | Enhanced institutional framework governing loan guarantees | Malawi, Senegal, Sierra Leone | 
Managerial structure | Upgraded or modernized organizational structure | Burundi, The Gambia, Ghana, Kenya, Maldives, Malawi, Tanzania, Senegal | 
 | Strengthened middle office | Bangladesh, Papua New Guinea, The Gambia, Liberia, Malawi, Nicaragua, Sierra Leone. Moldova | 
Debt Management Strategy | Debt management strategy development based on cost-risk analysis, strengthen debt management analysis | Bangladesh,B urkina Faso, Ethiopia, Maldives, Cape Verde, The Gambia, Ghana, Kenya, Malawi, Mali, Moldova, Mozambique, Nigeria, Nicaragua, Rwanda, Tanzania | 
Audit | Strengthened audit function | Malawi, Mongolia | 
Domestic Borrowing | Deepening domestic market development | Bangladesh, Kenya | 
Cash Flow Forecasting & Cash Balance Management | Strengthened cash management | Burkina Faso, Malawi, Maldives | 
Segregation of Duties, Staff Capacity & BCP | Reduced operational risk | Bangladesh, Bhutan, Maldives, Rwanda, Togo | 
Debt Records and Debt Reporting | Improved debt recording and reporting | Bhutan, Burundi, Liberia, Burkina Faso, Malawi, Mali, Mozambique, Nigeria, Togo | 
Notes: / This reflects areas where countries have taken explicit steps to enhance capacity; it does not measure the effectiveness or completeness of the steps taken. This is based on information at the time of a mission visit.
Source: DeMPA and Reform Plan updates, mission staff, and country authorities.

## Slide 15: Conclusions
Programmatic approach continues to bear fruit
  Greater number of reform plan mission than past, results from upstream assessment and analytical work increasingly taking root and triggering institutional reforms and capacity building
Reform momentum most sustained when strong links between upstream and downstream implementation activities and is consistent within the broader PFM reforms
Importance of maintaining integrity and quality of upstream work through independent assessments, peer review, and quality control process
DMF continues to strengthen coordinating mechanism among providers of providers of TA, development partners and donors

## Slide 16: Thank You
For more information:
http://www.worldbank.org/debt